## DOORS & CLM installation
Installation of DOORS
Sr no | Steps: | Time required:
1 | Choose 2 servers for installation which is properly configured and make sure server is having enough space | 15 mins
2 | Check system requirements.(http://www-969.ibm.com/software/reports/compatibility/clarity/index.html) | 15-20 mins
3 | Copy/Download installables | ~ 1 hour to copy/download each component.
4 | For DOORS installation, install DOORSDB, DOORSDWA and DOORS broker on the same server. Install DOORS interop on another server as recommnded by IBM. | ~1 hour( In case of any errors, we can expect more time)
5 | Configure DOORS DWA and interop 1. Edit festival.xml file 2. Edit server.xml file 3. Edit doorsredirector.properties file | 30 mins
6 | Start DWA, broker and Interop. | 10-15 mins
Installation of CLM applications
1 | Verify your hardware and software meets minimum system requirements. Check if java version is not supported, upgrade it. | ~30 mins
2 | Check that server is having enough space for the complete application setup. | 15 mins
3 | Install IBM Installation manager first | 10 mins
4 | Launch Installation manager and select every application which you would like to install. | 15-20 mins
5 | Once applications are installed, go for WAS(Web Spehere application servcies) configuration. | ~1 hour(In case of any errors, we can expect more time)
6 | JTS setup | ~1 hour
Application association
RTC->DOORS association
1 | Go to RTC->Application->Consumers->Provide consumer name & consumer secret. It will generate one provisional key from that. | 15-20 mins
2 | Go to DOORS->OSLC->Remote services->Add correct remote service link and cosumer key generated from RTC.
3 | Complete integration by adding DOORS details in RTC->Application->Friends.
RQM->DOORS association
1 | Go to RQM->Application->Consumers->Provide consumer name & consumer secret. It will generate one provisional key from that. | 15-20 mins
2 | Go to DOORS->OSLC->Remote services->Add correct remote service link and cosumer key generated from RQM.
3 | Complete integration by adding DOORS details in RQM->Application->Friends.
| Once application association has been done,associate particular RTC->RQM->DNG project as per the project requirement from the association tab. | 15-20 mins

## DOORS Programme creation
DOORS Programme creation
| Prerequisites | Location:
1 | Birth certificate | Location should be fix from where we can easily fetch these documents.
2 | csv file exported from RTC eclipse client
3 | Log file location | It should be predefined
Sr no | Steps
1 | Baseline all the modules of the project which you want to archieve
2 | Temporarily remove access for all non admins
3 | Archieve generic requirements dpa file and restore it by giving different name in different location.
4 | Upload filedAgainst information to project configuration module: Go to RTC eclipse client and navigate to your project. Map categories with the same team name. Export that structure with the help of export utility in form of excel. Go to categories tab in that excel sheet, change URL name as a filedAgainst & Names with the MFC DVP Team, delete every other columns and save it in a csv format.
5 | Setup Project configuration module: Go to DOORS->Admin folder->Open Project Configuration module. Select file->import -> import that sheet which is exported from RTC.
6 | Make sure application integration and specific DOORS->RTC project integration has been done properly .
7 | Set up RTC configuration template for the project. In the DOORS database explorer go to change management->define config template->create->select Oauth->Click next 4 times->Finish.
8 | Copy Configuration Module: Go to Change Management->Copy configuration module->Copy RTC configuration from the previous project to the recent project and then copy that configuration for every team.
9 | Create project specific groups In RDS if RDS is configured with DOORS
10 | Add Birth cerificate to Variants for input module: Go to Admin->Varients for input->Import varients for input file(Birth certificate provided by business)->Save->Close the module.
11 | Add varient information into Project configuration: (Go to Admin->Project configuration->RMDV Utilities->Admin->Add varient information to configuration module.) Verify that the script completes and varient information is added to module and save it.
12 | Run Create Programme script: Go to RMDV Utilities->Admin->Create programme You can check the log files on the defined location to see if there is any errors. Otherwise it will give script completed successfully prompt.
13 | Sync requirements from DOORS to RTC and associate test case with it to verify whether everything is running properly or not.